## Burndown Chart
Sprint Burndown Chart
Task ID | Task Description | Initial Estimate | 2022-11-04 | 2022-11-05 | 2022-11-06 | 2022-11-07 | 2022-11-08 | 2022-11-09
|  | Day 0 | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6
1 | Pesquisar Google Drive API | 4 |  |  | 1 | 1 | 1 | 1
2 | Elaborar user storie google drive | 2 | 1 | 1
3 | Pesquisar Google Drive API | 4 |  |  | 1 | 1 | 1 | 1
4 | Elaborar user storie google drive | 2 | 1 | 1
5 | Elaborar relatorio | 2 |  |  |  |  | 1 | 1
Completed Effort |  | 0 | 2 | 2 | 2 | 2 | 3 | 3
Remaining Effort |  | 14 | 12 | 10 | 8 | 6 | 3 | 0
Ideal Burndown |  | 14 | 13.0667 | 12.1333 | 11.2 | 10.2667 | 9.3333 | 8.4